## Executive Dashboard
MediCare Connect Executive GRC Dashboard — March 2026 | [7 empty] | Control Status | Count
Section | Metric | Value | RAG | Trend | Owner | Next Action | Due Date | Implemented | 5
OVERVIEW | Overall Compliance Posture | 54% | AMBER | UP | GRC Analyst | Close critical gaps | 2026-04-30 | Partial | 8
OVERVIEW | Audit Readiness Score | 48% | AMBER | UP | GRC Analyst | Complete evidence pack | 2026-05-15 | Missing | 5
OVERVIEW | Open Critical Risks | 5 | RED | FLAT | IT Manager | Treat top 3 risks | 2026-04-15
OVERVIEW | Open High Risks | 13 | AMBER | DOWN | IT Manager | Weekly risk review | 2026-04-10 | Risk Severity | Count
OVERVIEW | Overdue CAPA Items | 4 | AMBER | FLAT | GRC Analyst | Clear overdue actions | 2026-04-12 | CRITICAL | 5
POPIA | Information Officer Registered | NO | RED | FLAT | CEO | Register IO | 2026-04-05 | HIGH | 13
POPIA | 72h Breach Process Tested | YES | GREEN | UP | IO / IR Lead | Maintain readiness | 2026-09-30 | MEDIUM | 0
POPIA | Tier-1 Operator Agreements Complete | 40% | AMBER | UP | GRC Analyst | Sign PathLab DPA | 2026-04-20 | LOW | 0
ISO 27001 | Policies Approved | PARTIAL | AMBER | UP | CEO | Approve IS Policy pack | 2026-04-30
ISO 27001 | Control Implementation | 41% | AMBER | UP | IT Manager | MFA + encryption first | 2026-04-30
CLOUD | SOC2 Evidence Coverage | 61% | AMBER | UP | IT Manager | Close partial controls | 2026-05-30
VENDOR | Critical Vendors Assessed | 2 of 3 | AMBER | UP | GRC Analyst | Complete PharmaLink | 2026-05-10
IR | Tabletop Completed | YES | GREEN | UP | IR Lead | Track CAPA CA-001 to CA-005 | 2026-04-30
IR | Open Incident CAPA | 5 | AMBER | FLAT | GRC Analyst | Close MFA CAPA | 2026-04-15

## Control Tracker
Control ID | Domain | Control Name | Source Project | ISO 27001 | POPIA | Status | Maturity 1-5 | Owner | Evidence | Due Date | Commentary
CTL-001 | Governance | Information Security Policy | P1 | A.5.1 | Sec 19 | Partial | 2 | CEO | Policy draft | 2026-04-30 | Awaiting approval
CTL-002 | Governance | Information Officer appointed | P1 | A.5.2 | Sec 55 | Missing | 1 | CEO | Registration proof | 2026-04-05 | Critical legal gap
CTL-003 | Identity | MFA on privileged systems | P1/P5 | A.8.5 | Sec 19 | Partial | 2 | IT Manager | EVD-001 | 2026-04-15 | Root done; all users pending
CTL-004 | Endpoint | Laptop encryption | P1/P2 | A.8.24 | Sec 19 | Missing | 1 | IT Manager | BitLocker report | 2026-04-20 | Critical
CTL-005 | Logging | Event logging enabled | P1/P5 | A.8.15 | Sec 19 | Partial | 3 | IT Manager | EVD-004 | 2026-05-15 | CloudTrail on
CTL-006 | Backup | Tested backups | P2 | A.8.13 | Sec 19 | Partial | 2 | IT Manager | Restore test log | 2026-05-30 | Configured not tested
CTL-007 | Awareness | Security awareness training | P1 | A.6.3 | Sec 19 | Missing | 1 | HR | Attendance register | 2026-05-31 | Not started
CTL-008 | IR | Incident response plan | P4 | A.5.24-28 | Sec 22 | Implemented | 4 | IR Lead | IR plan + tabletop | 2026-09-30 | Tested
CTL-009 | Vendor | Supplier security management | P3 | A.5.19-22 | Sec 21 | Partial | 3 | GRC Analyst | VSAQ pack | 2026-05-10 | PathLab conditional
CTL-010 | Cloud | S3 public access block | P5 | A.8.10 | Sec 19 | Implemented | 4 | IT Manager | EVD-007 | 2026-03-31 | Complete
CTL-011 | Cloud | Encryption at rest | P5 | A.8.24 | Sec 19 | Implemented | 4 | IT Manager | EVD-006 | 2026-03-31 | Complete
CTL-012 | Access | Quarterly access review | P2/P5 | A.8.2 | Sec 19 | Missing | 1 | IT Manager | Review sheet | 2026-06-30 | Process needed
CTL-013 | Network | Restrictive security groups | P5 | A.8.20 | Sec 19 | Implemented | 4 | IT Manager | EVD-008 | 2026-03-31 | Complete
CTL-014 | Privacy | POPIA breach notification process | P4 | A.5.26 | Sec 22 | Implemented | 4 | Information Officer | Form 4 template | 2026-03-31 | Tested in tabletop
CTL-015 | Privacy | Operator agreements Tier-1 | P3 | A.5.20 | Sec 21 | Partial | 2 | GRC Analyst | Signed DPAs | 2026-04-20 | 1 outstanding

## Risk Summary
Risk ID | Risk Title | Inherent Score | Rating | Residual Score | Residual Rating | Status | Owner | Linked Controls | Treatment Due | Dashboard Flag
RSK-001 | Ransomware on PHRS | 25 | CRITICAL | 8 | MEDIUM | Open | IT Manager | MFA, EDR, Backup | 2026-04-30 | RED
RSK-002 | Stolen unencrypted laptop | 20 | CRITICAL | 4 | LOW | Open | IT Manager | BitLocker | 2026-04-20 | RED
RSK-003 | Phishing account takeover | 20 | CRITICAL | 6 | MEDIUM | Open | IT Manager | MFA, Awareness | 2026-04-15 | RED
RSK-004 | No registered Information Officer | 20 | CRITICAL | 3 | LOW | Open | CEO | IO appointment | 2026-04-05 | RED
RSK-005 | No IR / POPIA 72h process | 20 | CRITICAL | 6 | MEDIUM | Mitigating | IR Lead | IR plan | 2026-04-30 | AMBER
RSK-007 | Vendor without POPIA agreement | 15 | HIGH | 8 | MEDIUM | Mitigating | GRC Analyst | DPA + VSAQ | 2026-04-20 | AMBER
RSK-008 | Load shedding system impact | 15 | HIGH | 5 | LOW | Open | IT Manager | UPS/cloud failover | 2026-05-30 | AMBER
RSK-009 | Untested backups | 15 | HIGH | 4 | LOW | Open | IT Manager | Restore test | 2026-05-30 | AMBER
RSK-013 | SIM swap / weak OTP | 12 | HIGH | 4 | LOW | Open | Finance/IT | App MFA | 2026-04-30 | AMBER

## Vendor Status
Vendor ID | Vendor | Tier | Service | VSAQ Score | POPIA Agreement | Risk Rating | Status | Owner | Next Action | Due Date
VEN-001 | PathLab SA | Tier 1 | Pathology API | 68% | Pending | Medium | Conditional | GRC Analyst | Sign DPA + enforce MFA | 2026-04-20
VEN-002 | CloudMed Systems | Tier 1 | PHRS SaaS | 92% | Yes | Low | Approved | IT Manager | Annual reassessment | 2027-01-15
VEN-003 | PharmaLink SA | Tier 2 | e-Prescriptions | Under Review | Yes | Medium | In Review | GRC Analyst | Complete VSAQ | 2026-05-10
VEN-004 | NetCare Telecoms | Tier 2 | Connectivity | 84% | Yes | Low | Approved | IT Manager | Monitor uptime | 2026-11-10
VEN-005 | WasteCare SA | Tier 2 | Secure destruction | 88% | Yes | Low | Approved | Facilities | Annual cert check | 2026-10-05

## Incident & CAPA
Item ID | Type | Title | Source | Priority | Status | Owner | Opened | Due | Linked Risk | Notes
INC-2026-03-001 | Incident | Phishing simulation scenario | Tabletop | Critical | Closed | IT Manager | 2026-03-10 | 2026-03-20 | RSK-003 | Training case
CA-001 | CAPA | Enable MFA on Microsoft 365 | Tabletop | Critical | Open | IT Manager | 2026-03-12 | 2026-04-15 | RSK-003 | Highest priority
CA-002 | CAPA | Create evidence log template | Tabletop | High | Open | GRC Analyst | 2026-03-12 | 2026-04-10 | RSK-005 | In progress
CA-003 | CAPA | Pre-populate POPIA Form 4 | Tabletop | High | Open | Information Officer | 2026-03-12 | 2026-04-10 | RSK-005 | Template drafted
CA-004 | CAPA | Front-desk incident call script | Tabletop | Medium | Open | GRC Analyst | 2026-03-12 | 2026-04-30 | RSK-005 | Not started
CA-005 | CAPA | Enable DLP bulk export alerts | Tabletop | High | Open | IT Manager | 2026-03-12 | 2026-05-15 | RSK-003 | Planned
CA-006 | CAPA | Register Information Officer | Gap Assessment | Critical | Open | CEO | 2026-03-01 | 2026-04-05 | RSK-004 | Legal critical
CA-007 | CAPA | Sign PathLab POPIA DPA | Vendor Assessment | High | Open | GRC Analyst | 2026-03-10 | 2026-04-20 | RSK-007 | Conditional approval

## Cloud Evidence Status
Evidence ID | Control Theme | Description | Status | Linked Control | Last Reviewed | Owner | Portfolio Ref
EVD-001 | Identity | Root MFA enabled | Captured | CLD-002 | 2026-03-20 | IT Manager | Project 5
EVD-002 | Identity | Password policy | Captured | CLD-003 | 2026-03-20 | IT Manager | Project 5
EVD-003 | Identity | Least privilege IAM | Captured | CLD-001/004 | 2026-03-20 | IT Manager | Project 5
EVD-004 | Logging | CloudTrail enabled | Captured | CLD-006 | 2026-03-20 | IT Manager | Project 5
EVD-005 | Logging | Log validation | Captured | CLD-008 | 2026-03-20 | IT Manager | Project 5
EVD-006 | Encryption | S3 default encryption | Captured | CLD-009 | 2026-03-20 | IT Manager | Project 5
EVD-007 | Exposure | S3 block public access | Captured | CLD-010 | 2026-03-20 | IT Manager | Project 5
EVD-008 | Network | Restrictive SG rules | Captured | CLD-011 | 2026-03-20 | IT Manager | Project 5
EVD-009 | Network | No open admin ports | Captured | CLD-012 | 2026-03-20 | IT Manager | Project 5
EVD-010 | Monitoring | CloudWatch alarm | Captured | CLD-007 | 2026-03-20 | IT Manager | Project 5
EVD-011 | Backup | Backup configuration | Captured | CLD-013 | 2026-03-20 | IT Manager | Project 5
EVD-012 | Access Review | IAM credential report | Captured | CLD-005 | 2026-03-20 | IT Manager | Project 5

## POPIA Obligations
Obligation ID | POPIA Reference | Obligation | Current State | RAG | Owner | Evidence | Due Date | Notes
POP-001 | Sec 55 | Register Information Officer | Not registered | RED | CEO | IO registration proof | 2026-04-05 | Critical
POP-002 | Sec 19 | Security safeguards | Partial | AMBER | IT Manager | Controls + cloud evidence | 2026-05-30 | In progress
POP-003 | Sec 21 | Operator agreements | Partial | AMBER | GRC Analyst | Signed DPAs | 2026-04-20 | PathLab outstanding
POP-004 | Sec 22 | Breach notification process | Implemented | GREEN | Information Officer | IR plan + Form 4 | 2026-03-31 | Tabletop done
POP-005 | Sec 17 | Documentation of processing | Partial | AMBER | GRC Analyst | Processing records | 2026-06-30 | Need RoPA
POP-006 | Sec 18 | Data subject participation process | Missing | RED | Information Officer | DSAR procedure | 2026-06-15 | Not built yet
POP-007 | Sec 14 | Retention & disposal | Partial | AMBER | Records Owner | Retention schedule | 2026-07-31 | Healthcare retention rules
POP-008 | Sec 72 | Cross-border transfer controls | Partial | AMBER | IT Manager | Region hosting proof | 2026-05-31 | Prefer SA region

## Data Dictionary
Term | Definition | RAG Rule | Refresh Frequency | Source Project
RAG Red | Critical exposure or overdue legal/control failure | Immediate action required | Weekly | All
RAG Amber | Partial implementation or tolerable short-term risk | Action planned | Weekly | All
RAG Green | Implemented and operating with evidence | Monitor | Monthly | All
Overall Compliance Posture | Weighted % of key controls implemented | <50 Red; 50-79 Amber; 80+ Green | Weekly | P1 P5
Audit Readiness Score | Policies + risks + evidence + CAPA health | <50 Red; 50-79 Amber; 80+ Green | Bi-weekly | All
Critical Risk | Score 20-25 inherent | Must have active treatment | Weekly | P2
CAPA | Corrective and Preventive Action | Overdue = Amber/Red | Weekly | P4
Evidence ID | Unique proof artifact reference | Must map to control | Monthly | P5
Tier-1 Vendor | Processes special personal info or core clinical systems | Agreement mandatory | Monthly | P3